## Sheet1
Date | Time | Task | Type | Mins | Comment | Comment
26.09.2022 | 22:20 | Idea and Concept | Research | 60 | The Fundamental Idea and Some Conceptualisation and Research on Existing Inventions
27.09.2022 | 14:55 | Arduino Tutorial | Tutorial | 90 | Arduino Electronic Basics - Voltagies and Currents
28.09.2022 | 19:05 | Arduino Tutorial | Tutorial | 95 | Arduino Electronic Basics - Resistance and Microchip
29.09.2022 | 14:55 | Arduino Tutorial | Tutorial | 80 | Arduino Electronic Basics - First Circuits and Lab
29.09.2022 | 16:00 | Arduino Tutorial | Tutorial | 80 | Arduino Electronic Basics - Analog and Digital Signal and Components
30.09.2022 | 21:10 | Arduino Tutorial | Tutorial | 130 | Arduino Programmin Basics - Serial, PinMode, Basic C++ and Lab: LED Series
30.09.2022 | 23:20 | Arduino Tutorial | Tutorial | 95 | Arduino Programmin Basics - Functions and LED State Lab
01.10.2022 | 18:15 | Arduino Tutorial | Tutorial | 80 | Arduino Programmin Basics - 4 Different LED and Speaker Lab Project
01.10.2022 | 21:00 | Arduino Tutorial | Tutorial | 100 | Arduino Programmin Basics - Analog PINS, ADC, Speaker Frequency with Potmeter Lab
04.10.2022 | 18:30 | First Keyboard | Experiment | 120 | Create First Arduino Keyboard with 8 Keys that Can be Pressed Simultaneously. Keyboard State is Translated into a Byte.
05.10.2022 | 23:15 | Project Document Boilerplate | Documentation | 240 | Document Cover Page, Image and Quote, Complete Sketch of Paragraphs and Structure, Header, Footer, Pagination, Styling
06.10.2022 | 3:30 | Project Introduction | Documentation | 140 | First Sketch of the Introduction Section / Research on Instrument Taxonomy, History, Sound and Audio
06.10.2022 | 9:20 | Project Introduction | Documentation | 50 | First Version of the Background Paragraph
08.10.2022 | 16:00 | Project Introduction | Documentation | 60 | Outline of Specifications and Terminology: Chord, Riff, Monophone/Polyphone
09.10.2022 | 13:00 | Existing Technologies | Research | 190 | Existing Technologies, Guitar Hero, MI Digital Guitar, RockSmith and their specifications and Comparision Section
09.10.2022 | 22:00 | Project Aim and Objectives | Documentation | 80 | Research Gap, Aim and Objectives Paragraph, Literature Review: Sketch Strum vs Strumbar Task Plan
10.10.2022 | 12:00 | Research on Possible Solutions | Research | 45 | Read about Keyboard Matrixes and Keypress Ghositng, Forse Sensitive Resistors, Guitar Fret Distance Calculation Algorithms
11.10.2022 | 19:00 | Research Keyboards | Research | 80 | Research on Keyboard Scanning and Create Flowchart
11.10.2022 | 23:00 | Research Keyboards | Research | 240 | Research Key Switch Interface Design: Buses, Matrix, Debouncing
12.10.2022 | 3:30 | Research Fret Distances | Research | 210 | Research the Calculation and Algorithm of Fret Distances Create Diagrams and Paragraphs
12.10.2022 | 16:30 | Correcting Citations | Documentation | 25 | Correct citations with Microsoft World's automatic features
13.10.2022 | 10:30 | User Requirements | Research | 30 | Research User Requirements Formats and Best Practices
13.10.2022 | 12:30 | Prerequisites | Documentation | 30 | Write Prerequisites and Refine Concept Diaqgram
13.10.2022 | 13:30 | User Requirements | Documentation | 90 | User Requirements Hardware, Software, Authentication, Wireframes
13.10.2022 | 17:00 | User Requirements | Documentation | 170 | User Requirements: Sign in, Home Page Wireframes
13.10.2022 | 20:00 | User Requirements | Documentation | 240 | User Requirements: Play Menu Option, Play Wireframes, Experiment with Scoring Ideas, Scoring Table
14.10.2022 | 2:00 | User Requirements | Documentation | 130 | User Requirements: Complete
14.10.2022 | 10:00 | Constraints | Documentation | 55 | Constraints Chapter: Scope and Limitations
14.10.2022 | 14:00 | Cost, Marketability, Feasibility | Documentation | 220 | Chapters Cost (research prototype parts for estimation), Target Audience, Marketability, Feasibility and Social Aspects for Success
17.10.2022 | 11:30 | Risk Analysis | Documentation | 95 | Collect Relevant Risk Factors, Severity, Probability, and Organise it in a Table
17.10.2022 | 16:00 | Methodologies | Documentation | 190 | Research Methdologies Suitable for Individual Projects, Document Waterfall, TDD, KanBan, and Justify Chosen Methodologies
17.10.2022 | 20:00 | ProjectLibre | Tutorial | 20 | Tutorials on How to Use ProjectLibre Software
17.10.2022 | 20:20 | ProjectLibre | Documentation | 100 | Create Work Breakdown Structure and Gantt Chart with Project Libre
17.10.2022 | 22:00 | Literature Review | Documentation | 180 | Music Notations, Terminology, Keyboard Ghosting and Diagrams
18.10.2022 | 1:00 | Voltage Dividers | Research | 75 | Research on Voltage Dividers Circuits that Can Only Register one Value
20.10.2022 | 13:30 | Logarithmic Ladder | Research | 90 | Research on Logarithmic Ladder Solutions
20.10.2022 | 23:00 | Linear Ladder | Research | 210 | Research on Linear Laddre Solutions, Algorithms and Diagrams (Resistance Calculation)
21.10.2022 | 12:00 | Logarithmic Ladder | Research | 190 | Research on L Laddre Solutions Lab
21.10.2022 | 19:30 | Audio on the Browser | Documentation | 140 | Research and Write Audio on the Web Browsers Paragraph
22.10.2022 | 12:00 | Proposal First Draft | Documentation | 60 | Formatting, Citations, Appendix: Diagrams, Tables, Ethic Form
24.10.2022 | 17:00 | Matrix 4 x 4 | Lab | 90 | Try to create a 4 by 4 switch matrix (Fail)
26.10.2022 | 0:30 | Research 4 x 4 | Research | 45 | Youtube Tutorials: Research and Make Notes
29.10.2022 | 19:00 | Matrix 4 x 4 (2) | Lab | 130 | Try to create a 4 by 4 switch matrix (Success)
01.11.2022 | 0:01 | Videos on Wiring Design | Research | 110 | Youtube Research on Different Wiring Solutions for Button Matrix and Resistors
07.11.2022 | 19:00 | Arduino Matrix | Lab / Research | 230 | 9 by 3 (max) Matrix with Diodes (No Masking and Ghosting) and Input Pullup
13.12.2022 | 9:30 | Documentation Cover Page | Documentation | 180 | Create a Black and White Geometric Cover Page and Correct Cover Image Citations
14.12.2022 | 0:15 | Restructure Proposal Format | Documentation | 160 | Restructure the Whole Proposal to Follow Recommended Dissertation Format
14.12.2022 | 3:00 | Finalise Proposal | Documentation | 195 | Finalise Chapters and Improve / Extend Some Grammar and Sentencing Issues
16.12.2022 | 16:00 | Review Arduino Products | Research | 40 | Compare the Available Arduino Microcolntrollers before Purchase
16.12.2022 | 16:40 | Find Parts | Research | 20 | Find Shops that Sell Matte Black Carbon Fibre Sheets, and Electrical Components
16.12.2022 | 17:00 | Setup Development | Code | 60 | File Structure and Basic Layout of Landing Page
16.12.2022 | 18:00 | Main Menu | Code | 60 | Landing Page Main Menu
17.12.2022 | 16:00 | Profile / Recently Played | Code | 85 | Left Aside: Profile and Recently Played Front End Design
17.12.2022 | 23:00 | Album List Design | Code | 60 | Design the Boilerplate Album List CSS
18.12.2022 | 0:00 | Chords Json | Research | 20 | Find a Complete Collection of Chords for the Chord Finder Function
18.12.2022 | 0:20 | Import Chords JSON | Code | 40 | Embed the Whole 13MB Chords JSON in a JS Function that Returns an Object
18.12.2022 | 23:00 | Baseline Chords | Code | 420 | Create Chord Display Function (Works with Cords on the Base Line)
18.12.2022 | 19:00 | Chord Theory | Research | 35 | Read about Chord Naming Conventions and How to Dissect Them
19.12.2022 | 20:15 | Higher Fret Chords | Code | 90 | Finalise Chords for Other than Base 0 and Check for Multitouch Barre Finger Positions
19.12.2022 | 22:00 | Barre Chords | Code | 45 | Complete Chord Display for Multi Touch Barre Finger Positions
19.12.2022 | 23:00 | Chord Display Versions | Code | 210 | Create Display All and Selected Chords Versions
20.12.2022 | 2:30 | Chord Search | Code | 200 | Create Search Options: Base, Key, Search for Complete List or Handpicked Names
21.12.2022 | 14:00 | Searching for Components | Other | 140 | Visit OKGo Charing Cross Electric Shop (No Arduino Found)
22.12.2022 | 12:00 | Searching for Components | Other | 170 | Visit RC Component Surrey Quay Shop (No Arduino Found)
22.12.2022 | 14:30 | Serial Port | Research | 20 | Reading on Serial Port Connectivity and How to Connect to a Web Client
22.12.2022 | 15:00 | Arduino Push Button | Experiment | 20 | Build a Simple Arduino Circuit that Detects a Button Press and Displatches it on Serial Connection
22.12.2022 | 15:30 | Serial Communication | Code | 90 | Use NodeJS and Socket.io to Connect Arduino to Webbrowser (No Native Solution Built in)
22.12.2022 | 19:00 | Serial Communication Debug | Code | 200 | Backend Detects Serial Port, Socket Communication Fails (Unsuccessful Debugging)
22.12.2022 | 22:30 | Serial Communication Debug | Code | 60 | Backend Detects Serial Port, Socket Communication Fails (Successful Debugging)
23.12.2022 | 0:00 | Finalise Chord Search | Code | 270 | All Functionalities Done: Display, Set Root, Type, Base, Desktop Layout
23.12.2022 | 11:00 | Review Arduino Options | Research | 50 | Final Review of Leonardo, Mega and Due before Purchase
23.12.2022 | 13:30 | Purchase Components | Other | 95 | Purchase Arduino Due (Arduino.cc), 120 x Momentary Tactile Switches and N14007 Diodes, DuPont Wires 10m Multi Colour (Amazon)
23.12.2022 | 14:30 | Refresh Specification | Documentation | 25 | Add an Extended Chords Section
23.12.2022 | 16:00 | Create Gutiar Sound MP3s | Other | 185 | Create Guitar Notes from E2 to C6 with Audiacity
23.12.2022 | 20:10 | Play Chords on Click | Code | 70 | Calculate the Cord Notes from Positions and Play them in an Interval (Howler.js for Audio)
26.12.2022 | 12:10 | Guitar Body Design | Design | 20 | Find a Suitable Guitar Body Design (Chosen: Les Paul: Gibson SG SG)
26.12.2022 | 13:40 | Guitar Body Design | Design | 90 | Find Technical Drawing of Les Paul with the Right Measurement, Print, Cut Template
26.12.2022 | 17:10 | Standard Music Notation | Research | 80 | Check SMN for Writing the Tabulature Functionality
26.12.2022 | 19:00 | Tab Data Structure | Research | 155 | Create a Simple TAB Structure that Records Timing and Chords as well
26.12.2022 | 22:00 | Compose: Display Tabs | Code | 470 | Display Tablatures, Notes, Chords for Compose Menu Option
27.12.2022 | 12:30 | Compose: Tabs Offset | Code | 210 | Create Game Loop: Metronome, Offset to Center Active Tab Bar (Odd Centering)
27.12.2022 | 12:30 | Compose: Debug Centering | Code | 185 | Divide Centering and Playing into 1 Row and Multi Row, Unsuccessful Location of Actively Played Beat (Debug Continues)
28.12.2022 | 17:30 | Fret and Button Arrangement | Design | 270 | Experiment with Design Options / Create Technical Drawing of Exact Fret Distances, Botton Arrangement and Neck
28.12.2022 | 22:50 | Neck Board Drilling Drawing | Design | 50 | Add Drilling Technical Drawing
28.12.2022 | 23:40 | Array of Buttons 1 | Experiment | 95 | Create an Array of Buttons and Read State - Preparing Controller Programing (Uno Works) (Due Doesnt)
29.12.2022 | 1:35 | TroubleShooting Faulty Pin 1 | Troubleshooting | 140 | Hunting for Faulty PINS on New Arduino Due After an Insuccesful Transitioning From Arduino Uno ( Input D13 - D35 Tested OK)
29.12.2022 | 4:00 | Design and Dev Chapters | Documentation | 75 | Create a Complete Header Structure Template for Design, Development and Testing Chapters (For Semester 2)
29.12.2022 | 14:30 | Buy Plastic and Adhesive Material | Other | 90 | Visit Denny's Plastic (Closed), Leylands: 1220mm x 610mm x 2mm Polysterine Sheet, Matt Black Spray Paint, Drill Bits (1,2,3mm), Gorilla Gel, CT1 Clear
29.12.2022 | 16:00 | Cut Out Neck | Build | 45 | Neck with 2mm Seems too Thin Because the Plastic Sheet is Chipping off when Cutting
30.12.2022 | 15:00 | Buy Plastic Sheet 2 | Other | 30 | Buy 3mm Plastic Sheet
30.12.2023 | 16:00 | Cut Out Neck 2 | Build | 55 | Cut a 50mm x 48mm Piece and Smoothen the Edges, and Sand Surface, Paint to Matte Black
30.12.2024 | 18:00 | Grooves for Frets | Build | 300 | Cut Grooves for the Fret Pieces (Fret 20 - 16 Done, Needed to Stop because of Noise)
30.12.2025 | 23:00 | Lengthen Button Legs | Experiment | 30 | Try to Lengthen a Buttons Leg with Solder and Wire as the Sheet is 3mm just Like the Legs (Working with Soldering Iron without a Table Vice is a Torture)
30.12.2026 | 23:30 | TroubleShooting Faulty Pin 2 | Troubleshooting | 50 | Hunting for Faulty PINS on New Arduino Due Continued ( Input D36+ ) Faulty Pins D36 - D53, We have 26 Working Digital Pin Left
31.12.2027 | 0:20 | Arduino Play Sound | Experiment | 60 | Create a Circuit that Releases a Button Press, Listen to Keyboard on Website and Play a E2 Note (Works)
31.12.2028 | 1:20 | Browser Audio Delay | Troubleshooting | 140 | Audio has a Significant Delay (~100 - 200ms) that Originates from How Browsers are Handling / Preloading Audio (Not Solved! Catastrophic if Remains Unsolved!!!)
31.12.2029 | 3:00 | WebAudio API | Research | 85 | Try to Search a Solution Using WebAudio API (Read Documentation, Watch Videos)
31.12.2030 | 14:00 | Buy Electric Saw | Other | 65 | Buy Electric Saw, Table Vice, and File
31.12.2030 | 16:00 | Cut Leftover Frets | Build | 300 | Cut the Rest of the Frets and Cut Fret Pieces 6 x 48mmm 20 Plastic Components
01.01.2023 | 15:00 | Paste Frets | Build | 75 | Paste and File Frets with a Rounded Bottom and a 45 Degree Angle on Top
01.01.2023 | 16:15 | Drilling Template | Design | 35 | Create a Drilling Template Using Draw.io and Print Out 20 Templates for Each Fret
01.01.2023 | 16:50 | Drill Holes for Button Legs | Build | 310 | Drill 480 Holes (120 Buttons x 4 Legs) (The Template Moved While Drilling and Resulted Some Disastrous Inaccuracies That Need Correction)
01.01.2023 | 23:00 | Repaint | Build | 20 | Smoothen the Surface of the Neck and Repaint it
02.01.2023 | 16:50 | Test Audio Delay on Web Apps | Test | 25 | Test Multiple Audio Based Web Apps (Guitar / Piano) to Reproduce Delay (No Significant Delay Found on Other Devices, After Restart My Machine Had No Delay)
02.01.2023 | 2:10 | Refactor Lab Matrix 1 | Lab | 90 | Refactor 3 by 10 Switch Matrix for the Correct Pin Position (Horizontal Buttons as Neck Width is 48mm and Vertical Arrangement is Cumbersome) Part 1
03.01.2023 | 15:00 | Cut Out Neck 3 | Build | 90 | Second Try (Previous Attempt Was Inaccurate): Cut a 600mm x 50mm Piece of Plastic
03.01.2023 | 16:30 | Cut Out Frets 2 | Build | 270 | 50mm x 5mm Pieces of Frets x 21 (Need an Extra One for Fret 0)
03.01.2023 | 21:00 | Fret Edges and Grooves | Build | 75 | Add 6 Grooves (Dist 5, 13, 21, 29, 37, 45) for Strings and Add a 45deg Angle for Edges
03.01.2023 | 23:00 | Microcontroller Single Button | Code | 60 | Create a Simple Button Push (Character "P") Event and Experiment with Timing and Delay
04.01.2023 | 0:00 | Facvicon | Design | 30 | Create favicon.png (6 Lines with the Colors Used for Strings [Yellow, Orange, Pink, Purple, Blue, Green])
04.01.2023 | 0:30 | Jam Guitar | Code | 210 | Write a Guitar Display Function for the Jam Option that Shows Strings and Frets
04.01.2023 | 4:00 | Profile UserBadges | Code | 50 | Create Three Profile Badges (Hard Coded So Far)
04.01.2023 | 4:50 | Index Background Img | Code | 85 | Find an Appropriate Black Transparent Concert Background and Blend it into the Main Menu Bottom Section and Arrange Menu Layout
04.01.2023 | 16:00 | Draw Measurements | Build | 65 | Draw Fret Distances and Button Leg Drill Holes on the Neck
05.01.2023 | 10:00 | Drill Holes for Button Legs 2 | Build | 300 | Drill 480 Holes (120 Buttons x 4 Legs) Second Attempt, Used a 2mm Drill Head Instead of 1.5mm to Leave Space for Soldering
05.01.2023 | 16:00 | Grooves for Frets 2 | Build | 300 | Cut Grooves for the Fret Pieces
05.01.2023 | 21:00 | Paste Frets 2 | Build | 60 | Paste and File Frets with a Rounded Bottom and a 45 Degree Angle on Top, Paint Neck
05.01.2023 | 23:15 | Solder Buttons to Neck | Build | 75 | Solder on Button Legs to Wires and Pull through Neck (Btn 1 - 3) / Frets Seem to Be Too Low This Time
06.01.2023 | 0:30 | Write Controller Listener | Code | 270 | Listener for Keypress Events and Translate a Sequence of Characters that will Come from the Controller into Fret and Strum Actions (Play Music with Keyboard)
06.01.2023 | 12:30 | First Row of Btn Matrix | Build | 60 | Try to Create the First Row of the Button Matrix on the Neck, Start from Fret 20
06.01.2023 | 19:30 | Microcontroller Programming | Coding | 50 | Program Arduino to Display Presses on a Matrix of Buttons (20 x 6)
06.01.2023 | 12:30 | First Row of Btn Matrix 2 | Build | 580 | Trying to Find a Solution How to Efficiently Connect Components (Lots of Trouble, 2 Buttons Work from 6)
07.01.2023 | 16:30 | Universal PCB | Design | 50 | Design an Electric Solution that Works on a Universal Prined Circuit Board (Previous Wiring Attemps are Messy and Unraliable, Near Impossible to Execute)
07.01.2023 | 19:00 | Search Universal PCB | Other | 30 | Search for an Appropriate PCB that is Smaller or Equal to 50mm in One Dimensoin (40mm x 60mm Black PCB Found and Ordered)
08.01.2023 | 21:00 | Proofread Proposal | Documentation | 70 | Proofread and Correct Grammar, Citation, Update Logbook and Submit Dissertation Proposal
09.01.2023 | 3:30 | Redesign PCB | Design | 65 | Redesign How Components will Connect on the Circuit Board (Trying to Find an Efficient Way with Fewer Space Requirement)
10.01.2023 | 15:15 | Redrill Button Holes 1 | Build | 150 | Drill Wider Button Holes (2mm x 3mm) on Frets 20 - 9
10.01.2023 | 22:20 | Fret Design Diagram | Design | 50 | Create a Fret Design Projection Diagram
10.01.2023 | 23:25 | Electric Circuit Diagram | Design | 60 | The Current Design Includes All the Fret/String (aka Row and Column) Connections, Buttons, Diodes and Microcontroller, But Lacks the Strum and LEDs
11.01.2023 | 0:30 | Neck Design Diagram | Design | 80 | Create a Projection Design for the Neck, Frets and Drills
11.01.2023 | 2:30 | Neck Cover Design Diagram | Design | 110 | Create a Projection Design for the Neck Cover, Screws, Washers, Nuts and Assembly
11.01.2023 | 4:00 | Les Paul Body SVG | Design | 120 | Create an SVG File of the Guitar Body Outline Using the Les Paul Illustrator Technical Drawing and Crop it to Size to Use for Diagramns
11.01.2023 | 19:00 | 2 x 2 Matrix Design | Lab | 60 | Create a Simulation of a Small Matrix to Copy for Soldering
11.01.2023 | 20:00 | 2 x 2 Matrix BreadBoard | Experiment | 120 | Martix Works at the Beginning and Fails Soon After (Column Pins Stuck at HIGH State)
11.01.2023 | 22:00 | Single Button State Change | Experiment | 130 | Create a Single Button that Changes State to Check if Pins are Able to Change State, Build Circuit to Test (Works)
12.01.2023 | 0:10 | 2 x 2 Matrix Troubleshoot | Troubleshooting | 290 | Build 2 x 2 Software and Hardware Parts from Scratch (Fail to Change Button States, Tried Every Possible Scenario, Maybe Microcontroller is Faulty?)
12.01.2023 | 13:30 | Faulty BreadBoard | Troubleshooting | 30 | Conducting Some Further Experiments Found that the Breadboard Connections are Failing in Most Joints (There May be Other Problems as Well)
12.01.2023 | 14:00 | 4 x 4 PCB Matrix | Experiment | 100 | Create a 4 x 4 Button Matrix with a Universal PCB to Prove that Breadboard is Faulty (Successful 4 x 4 Implementation)
12.01.2023 | 19:00 | Redrill Button Holes 2 | Build | 65 | Drill Wider Button Holes (2mm x 3mm) on Frets 8 - 1
12.01.2023 | 20:10 | Glue PCBs | Build | 20 | Glue the Universal PCBs on the Back of the Neck
12.01.2023 | 20:30 | Drill PCB | Build | 45 | Drill the PCBs through the Button Holes with 1.5mm Drill Bit, that will just be OK to Put the Wire through
12.01.2023 | 10:00 | BUS Wiring | Build | 80 | Cut, Paste and Solder Wires 10 Colour Coded Wired from Microcontroller to Neck
12.01.2023 | 11:20 | Button e20 | Build | 40 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
12.01.2023 | 12:40 | Button B20 | Build | 80 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
12.01.2023 | 14:00 | Button G20 | Build | 50 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
12.01.2023 | 16:30 | Button D20 | Build | 110 | Button D20 ans Rest of the Row Pin BUS
12.01.2023 | 18:50 | Button A20 | Build | 30 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
12.01.2023 | 19:20 | Button E20 | Build | 20 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
12.01.2023 | 19:40 | Finalise Column | Build | 50 | Test Buttons on Fret 20 and Fix Up Button Positions to the Neck
12.01.2023 | 20:30 | Prepare 6 Buttons for Fret 19 | Build | 45 | Prepare Button Legs, 3 Extention Wire for 6 Buttons
13.01.2023 | 21:25 | Button e19 | Build | 30 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
13.01.2023 | 22:20 | Button B19 | Build | 20 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
13.01.2023 | 22:40 | Button G19 | Build | 10 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
13.01.2023 | 22:50 | Button D19 | Build | 20 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
13.01.2023 | 23:35 | Button A19 | Build | 30 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
13.01.2023 | 23:40 | Button E19 | Build | 15 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
15.01.2023 | 16:00 | Take Apart Prev Solution | Build | 40 | The Previous Solution Works, But So Clunky and Disorganised that Impossible to TroubleShoot, Start Again from Scratch
16.01.2023 | 18:00 | Button e20 | Build | 30 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
16.01.2023 | 21:10 | Button B20 | Build | 30 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
16.01.2023 | 21:40 | Button G20 | Build | 25 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
16.01.2023 | 22:20 | Button D20 | Build | 20 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
16.01.2023 | 22:45 | Button A20 | Build | 25 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
16.01.2023 | 23:10 | Button E20 | Build | 20 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
16.01.2023 | 23:35 | Button e19 | Build | 25 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
17.01.2023 | 0:00 | Button B19 | Build | 20 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
17.01.2023 | 0:25 | Button G19 | Build | 45 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
17.01.2023 | 1:20 | Button A19 | Build | 45 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
17.01.2023 | 2:05 | Button D19 - E18 | Build | 270 | Add Button (Straigthen Legs and Solder 3 Extention Wires, Glue Button to Place, Connect IN Wire, Connect Row Wire to a Diode, Diode to Row BUS, Test Button)
17.01.2023 | 17:00 | Row 17 | Build | 100 | Add 6 Buttons with Diodes and Connect them (Follow Above Steps)
17.01.2023 | 19:45 | Row 16 | Build | 150 | Add 6 Buttons with Diodes and Connect them (Follow Above Steps)
17.01.2023 | 23:15 | Row 15 | Build | 130 | Add 6 Buttons with Diodes and Connect them (Follow Above Steps)
18.01.2023 | 1:25 | Row 14 | Build | 110 | Add 6 Buttons with Diodes and Connect them (Follow Above Steps)
18.01.2023 | 18:10 | Row 13 | Build | 130 | Add 6 Buttons with Diodes and Connect them (Follow Above Steps)
18.01.2023 | 20:25 | Row 12 | Build | 120 | Add 6 Buttons with Diodes and Connect them (Follow Above Steps)
18.01.2023 | 22:55 | Row 11 | Build | 110 | Add 6 Buttons with Diodes and Connect them (Follow Above Steps)
19.01.2023 | 1:00 | Bus Cable for 10 - 1 | Build | 130 | Cut, Paste and Solder Wires 10 Colour Coded Wired from Microcontroller to Neck
19.01.2023 | 3:30 | Row 10 Part 1 | Build | 90 | Add 6 Buttons with Diodes and Connect them (Follow Above Steps)
19.01.2023 | 18:45 | Strip Wires for Row 10 - 9 | Build | 45 | Spare Some Time and Prepare for Next Fret Wires
19.01.2023 | 20:25 | Row 10 Part 2 | Build | 45 | Add 6 Buttons with Diodes and Connect them (Follow Above Steps)
19.01.2023 | 21:15 | Row 9 | Build | 100 | Add 6 Buttons with Diodes and Connect them (Follow Above Steps)
20.01.2023 | 0:15 | Row 8 | Build | 150 | Add 6 Buttons with Diodes and Connect them (Follow Above Steps)
20.01.2023 | 19:00 | Row 7 | Build | 115 | Add 6 Buttons with Diodes and Connect them (Follow Above Steps)
20.01.2023 | 21:40 | Row 6 | Build | 85 | Add 6 Buttons with Diodes and Connect them (Follow Above Steps)
20.01.2023 | 23:50 | Clear Controller Code | Code | 45 | Refactor the Whole Micro Controller Code
21.01.2023 | 0:45 | Read Fret State | Code | 50 | Store the Old State of the Controller and Read the New One, Create Furter Controller States: ON/OFF, Transaction, Power
21.01.2023 | 1:35 | Monitor State Changes | Code | 50 | Compare Old State Against the New One and Return a Boolean
21.01.2023 | 2:25 | Create Protocol | Code | 30 | Create a Communication Protocol Between Console and User Device
21.01.2023 | 3:30 | Send Keyboard Message | Code | 70 | Send a Keyboard Message about State Changes on Controller's Fret Buttons Using a Simplistic Protocol
21.01.2023 | 4:05 | Controller Event Handler | Code | 95 | Create an Event Handler that Records Each String Upper Most Positions and React to a Strum Event
21.01.2023 | 12:15 | Row 5 | Build | 120 | Add 6 Buttons with Diodes and Connect them (Follow Above Steps)
21.01.2023 | 15:30 | Row 4 | Build | 95 | Add 6 Buttons with Diodes and Connect them (Follow Above Steps)
21.01.2023 | 17:20 | Row 3 | Build | 105 | Add 6 Buttons with Diodes and Connect them (Follow Above Steps)
22.01.2023 | 19:20 | Row 2 | Build | 120 | Add 6 Buttons with Diodes and Connect them (Follow Above Steps)
22.01.2023 | 21:20 | Row 1 | Build | 200 | Add 6 Buttons with Diodes and Connect them (Follow Above Steps)
24.01.2023 | 13:00 | Cut Body Front Cover 1 | Build | 70 | Attempt Failed, Material is Cracked and Broken Off While Cutting Curve
30.01.2023 | 15:30 | Cut Body Front Cover 2 | Build | 220 | Use Handheld Drill to Mill Out Unregular Curves
30.01.2023 | 19:30 | Cut Body Back Cover | Build | 100 | Use Handheld Drill to Mill Out Unregular Curves (Found the Right Technique to Mill Curves)
31.01.2023 | 13:30 | Body Sanding | Build | 120 | Sand Front and Back Cover Sheet from Rough Edges and Make them Perfectly the Same Size
31.01.2023 | 15:30 | Sheet Sanding | Build | 30 | Sand the Surface of Front and Back Sheet so it Will be Easier to Paint and Glue
31.01.2023 | 16:00 | Cut Wall | Build | 90 | Cut a 44mm x 150mm x 2mm Piece of Sheet for the Side of the Guitar Body
31.01.2023 | 17:30 | Sand Side Wall | Build | 20 | Sand the Guitar Side Wall Sheet
31.01.2023 | 18:35 | Band Side to Shape | Build | 175 | Bend the Plastic Sheet According to the Curvature of the Guitar Body Using Heat. Failed, Plastic Sheet Bending is Difficult to Controll, Cracks or Melts
31.01.2023 | 23:45 | Fundamental Design Paragraphs | Documentation | 165 | Design Introduction, Controller Design, Phisical Design and Electrical Housing, Les Paul Paragraph
01.02.2023 | 2:35 | Left Hand Paragraphs | Documentation | 110 | Drilling Instructions, Parameters, Neck Design, Neck Cover Design
01.02.2023 | 4:25 | Left Hand Electrics | Documentation | 65 | Electric Design, Options, Reasoning, Pros and Cons
02.02.2023 | 15:00 | Cut Template Foundation | Build | 60 | Cut 4 x 46mm x 80mm x 660mm Wood Slates as a Foundation for Guitar Body Templates for Bending
02.02.2023 | 16:00 | Paste Template Blocks | Build | 20 | Paste the Template Blocks Together with CT1 and Leave them to Dry Min 24 Hours
02.02.2023 | 17:30 | Cut Body Side Walls 1 | Build | 50 | Cut 2mm x 1500mm x 45mm Plastic Side Walls (Material Broke while Cutting)
02.02.2023 | 19:00 | Cut Body Side Walls 2 | Build | 180 | Cut 3mm x 1500mm x 45mm Plastic Side Walls (Success)
03.02.2023 | 13:00 | Template Shaping 1 | Build | 60 | Cut the Guitar Shape Out of the Wooden Template
04.02.2023 | 11:45 | Template Shaping 2 | Build | 55 | Cut the Guitar Shape Out of the Wooden Template
04.02.2023 | 12:45 | Sand Template | Build | 100 | Send Template to Fit Guitar Shape as Perfectly as Possible
05.02.2023 | 14:30 | Side Wall for Neck | Build | 60 | Cut Side Wall for Neck According to the Design
05.02.2023 | 15:30 | Sand Wall for Neck | Build | 50 | Sand Wall for Neck
05.02.2023 | 16:35 | Cut Space for String Unit | Build | 50 | Cut Out a Rectangle of the Body Front Cover 80mm x 130mm for the String Unit
05.02.2023 | 17:35 | Bend Side Wall | Build | 235 | Bend Side Wall Using the Template and Heat (Many Failde Attempts: Hair Dryer, Hair Curler, Hair Straightener, Hot Water, Open Flame) Small Hair Drier Worked
05.02.2023 | 21:45 | Paste Side Wall | Build | 120 | Paste Side Wall to the Body (Needed Assistance to Hold / Force it into Place)
06.02.2023 | 12:45 | Smoothen Side Curves | Build | 120 | Fill Up Uneven Surfaces and Misbent Curves Using Porcelain Solution and UV Light
07.02.2023 | 13:00 | Body Support Pieces | Build | 280 | Create Support Pieces to Hold Body Back Cover, Drill and Paste Nuts to it
07.02.2023 | 18:00 | Paste Support Pieces | Build | 90 | Paste Support Pieces Together
07.02.2023 | 21:00 | Clean Neck | Build | 30 | Clean Neck Edges and Sides to Create an Even Surface for Gluing
07.02.2023 | 21:30 | Test Left Hand Control | Test | 25 | Test Left Hand Control Before Pasting Sides (All Good)
07.02.2023 | 21:00 | Paste Side Walls | Build | 20 | Paste the 2 Sides of the Neck
08.02.2023 | 9:30 | Drill Body Back Cover | Build | 35 | Drill Holes to Attach Body Back Cover
08.02.2023 | 10:35 | Fix Cover | Build | 90 | Fill Up Uneven Surfaces and Misbent Curves Using Porcelain Solution and UV Light as Cover Did Not Fit Properly
08.02.2023 | 13:15 | Cut Neck Cover | Build | 30 | Cut 2mm x 50mm x 500mm Plastic Sheet for Neck Back Cover
08.02.2023 | 13:50 | Neck Support Pieces | Build | 120 | Create Support Pieces to Hold Neck Back Cover, Drill and Paste Nuts to it
08.02.2023 | 16:00 | Cut Body for Neck | Build | 110 | Cut out the Appropriate Space from the Instrument Body to Paste the Neck
08.02.2023 | 18:00 | Paste Neck | Build | 120 | Paste the Neck to the Body, Fix them Together, Cut and Paste Supporting Material Such as Curved Plastic Piece and Straight Pieces
08.02.2023 | 20:10 | Sand Body | Build | 35 | Sand Rough Edges on Body
08.02.2023 | 21:00 | Place Microcontroller | Build | 30 | Cut Small Screws and Paste Nuts to Hold Microcontroller in Place in the Body
08.02.2023 | 21:30 | Fix Left Hand Control | Troubleshooting | 45 | Fix Contact Failure Caused by Pasting the Neck (Fret 7 on String e)
09.02.2023 | 9:30 | Neck Fix Up | Build | 90 | Fill Up Uneven Surfaces and Misbent Curves Using Porcelain Solution and UV Light as Neck Attechment Had Holes and Looked Horrid
09.02.2023 | 13:30 | Sand and Paint Guitar | Build | 130 | Final Sanding and Apply Matte Black Paint (With the Black Paint Every Sanding Mistakes are Visible, Need a New Round Later)
09.02.2023 | 18:00 | Cable Arrangement | Build | 30 | Fix Up and Arrange Cabling in the Body Neatly
09.02.2023 | 17:00 | LED Holes | Build | 25 | Drill Holes for LEDs and Fix Up Toggle On Off Switch
09.02.2023 | 19:30 | USB Hole | Build | 25 | Mill USB Hole and Drill for Screws, Fix Up A to B Converter
09.02.2023 | 22:10 | Plan LED Wiring | Lab | 25 | Create a TinkerCad Plan for the Toggle and LED Wiring
09.02.2023 | 22:35 | Wire LEDs and Toggle 1 | Build | 115 | Solution Does Not Work, Need Trouble Shooting
10.02.2023 | 1:00 | Start Hardware Dev Chapter | Documentation | 55 | Write Starting Chapter of Hardware Development (Mention KanBan, Fix Grammatical Errors in Prev Chapters, Add Appendix Gallery Table Row with an IMG Icon)
10.02.2023 | 16:45 | Wire LEDs and Toggle 2 | Build | 155 | Use Universal PCB to Hold LEDs in Place, 220 Ohms Resistors for Safety, and Connect Toggle. Write a Sample Blink Code and Toggle Read to Test Circuitry
10.02.2023 | 21:50 | Code Toggle and LEDs | Code | 85 | Red and Green LED is ON Depending on Toggle State, Blue LED is on When User Interacts with Fretboard (And Strum in Future Development)
11.02.2023 | 11:10 | Scetch Strum Unit | Design | 20 | Create a Basic Scetch of the Strum Unit Design
11.02.2023 | 12:20 | Order New USB Cable | Other | 25 | Order 3m Spring Coiled A 3.0 USB Cable and USB 3.0 Male to Male Converter
11.02.2023 | 13:00 | Strum Component #1 A | Build | 25 | Use 3mm Plastic: Cut ans Sand a 65mm x 15mm x 100mm Rombus Piece
12.02.2023 | 14:00 | Order Tactile Swich Caps | Other | 20 | Order 150 Pieces of Round Black Tactile Switches 6mm x 6mm with 3.2mm Diameter Hole
15.02.2023 | 10:30 | Strum Component #2 | Build | 155 | An Irregular Shape 3mm Plastic: Main Axis 125mm x 95mm with 45 Degree Angles
15.02.2023 | 13:30 | Buy Paint, Varnish, etc | Other | 20 | Matte, Paint, Matte Varnish, Washers, Sand Paper
15.02.2023 | 13:55 | Strum Component #3 A & B | Build | 55 | Irregular Shape that Use 3mm Plastic: 65mm x 15mm x 100mm Rombus Piece Top and 45mm x 15mm x 100mm
15.02.2023 | 14:50 | Strum Component #1 B | Build | 25 | Use 3mm Plastic: Cut ans Sand a 65mm x 15mm x 100mm Rombus Piece and Sand All Components together
15.02.2023 | 15:25 | Strum Component #4 | Build | 20 | 3mm Plastic: Rectangle 45mm x 122mm
15.02.2023 | 15:40 | Strum Component #5 A & B | Build | 20 | 3mm Plastic: Cut and Sand a 65mm x 15mm x 100mm Rombus 2 Pieces
15.02.2023 | 16:00 | Sand Components #4 and #5 A B | Build | 35 | Sand Together #4 and #5 Components to Ensure Better Alignment
15.02.2023 | 17:15 | Glue Components | Build | 55 | Paste All Components Together #1 - 5
15.02.2023 | 18:50 | Sand Washers | Build | 10 | Washers Must Have a Flat Side
15.02.2023 | 19:00 | Grooves for Strings | Build | 30 | String Grooves are 10mm Apart
15.02.2023 | 19:30 | Strum Component #6 A & B | Build | 50 | Screw Holder, Identical to #1
15.02.2023 | 20:20 | Drill Screw Holes | Build | 60 | Drill 6 x Min 9mm Hole with Certail Angles
15.02.2023 | 21:20 | Strum Component #7 A & B | Build | 15 | Small 5mm x 5mm Triangles
15.02.2023 | 21:35 | Sand and Paint Strum Unit | Build | 65 | Sand Surfaces Facing User and Apply Paint on Every Component Including Strings and Nuts and Washers (Except Screws)
15.02.2023 | 23:50 | Right Hand Control Design | Documentation | 35 | Write Intro Paragraph for Right Hand Design
16.02.2023 | 1:25 | Body Design Diagram | Design | 35 | Design the Diagram from the Paper Documentation (Cutting and Drilling Instructions)
16.02.2023 | 2:00 | Fret Electric Diagram 2x6 | Design | 25 | Design the Diagram from the Paper Documentation (Electrics Break Down)
16.02.2023 | 2:35 | Body Design Paragraph | Documentation | 50 | Write about Body Support Elements and Neck Weakness
16.02.2023 | 3:25 | Body Support Pieces Diagram | Design | 50 | Create a Diagram from Inside the Body that Displays All Supporting Material Used
16.02.2023 | 4:15 | Design Options Paragraph | Documentation | 50 | Options: Vibration and Pressure Sensors, Guitar Hero Strum Bars, Tactile Switches, String Switches
16.02.2023 | 12:30 | Resand and Readjust | Build | 120 | Resand the Whole Strum Unit as the Painting Ruined by Rain, Readjust Holes and Some Shapes
16.02.2023 | 14:30 | Alternative Strum Solution | Build | 250 | Find an Other Solution for Strumming as Wider Strings Do Not Bounce Back After a Strum
16.02.2023 | 18:40 | String Tuning Pegs | Build | 90 | Cut of Screw Heads as They Don’t Fit Perfectly
16.02.2023 | 20:10 | Strum Switch Levers | Build | 125 | 6 x 2mm x 10mm x 20mm Levers with 2 x 3mm Diameter Holes
16.02.2023 | 23:40 | Assemble Strum Unit | Build | 35 | Put Tuning Pegs, Nuts, Springs and Washers Together and Fix Up 6 Buttons
17.02.2023 | 0:20 | Wire Buttons | Build | 75 | Connect Strum Button Legs to an Extention Wire x 12 and Lead Them Through the Back Side of the Strum Unit
17.02.2023 | 2:00 | Strum Wiring Simulation | Lab | 50 | Simulate the Wiring of the Strum Solution Before Implementation to Reduce Debugging Time
17.02.2023 | 2:50 | Wire Strum Unit Completely | Build | 105 | Use Universal PCB to Connect Button Extention Wires to Ground and PINs
17.02.2023 | 3:35 | Test Strum Unit Electronics | Test | 20 | Test Failed, No Events Are Firing
17.02.2023 | 4:55 | Find Strum Unit Error | Troubleshooting | 20 | Contact Failure of Ground Wire Fixed
17.02.2023 | 5:15 | Test Strum Mechanism | Test | 30 | Test Levers and Springs: Mechanism Working, Many Adjustment Need to Be Done to Fine Tune It (Slightly Damaged a Button with Tuner Pressure)
17.02.2023 | 12:30 | Buy Steel Strings | Other | 25 | Soft Nickel Strings Suitable for Electric Guitars
17.02.2023 | 13:00 | String Up and Tuning | Build | 135 | Cut Small Springs for Levers (Pen Springs), Sand Off Levers, String Up Device, Mitigate Sound by Foam Padding
17.02.2023 | 22:20 | Program Strum Input | Code | 55 | Recognise State Changes on Strum Inputs, Display Active ON Status on LED and Send Changes Through USB Keyboard Using the Predefined Protocol
17.02.2023 | 23:30 | Jam Option: Make Some Noise | Code | 20 | Make Some Changes in Code to be Able to Try Out the Controller the First Time (Success, With Some Quirkiness Around Buttons and Strins)
18.02.2023 | 0:15 | Jam Option: Display Note | Code | 285 | Semi-Highlight Notes Pressed on the Fret Board and Highlight Strummed Fret and Strum Button and String
18.02.2023 | 4:00 | Jam Option: Stop Notes 1 | Code | 45 | Stop Notes from Playing When Strum is Pressed Again
18.02.2023 | 4:45 | Protocol Diagram | Documentation | 55 | Create a Diagram Explaining the Protocol Used for USB Keyboard Communication
19.02.2023 | 14:00 | Guitar Fixup | Build | 155 | Fix Up Issues: Missing Screws on Body and Neck, Contact Failures (B2 and Simultaneous A#2 D#3), Missing Supporting Element on Neck
20.02.2023 | 16:30 | Practice 1: General | Test | 80 | Get Familiar with the Instrument and Find Improvements
20.02.2023 | 18:40 | Measure Audio Delay | Code | 20 | There is No Significant Time Delay (1 - 3ms), So the Delay Problem May be Caused by Something Else
20.02.2023 | 19:00 | Troubleshooting Audio Card | Troubleshooting | 55 | Try Application on Other Devices: Significantly Less Delay (App is Fast Enough), Audo Card May be a Source of the Delay (Fixed: Firefox was the Issue)
20.02.2023 | 22:00 | Jam Option: Stop Notes 2 | Code | 50 | Stop Notes from Playing When Finger Released on Position
20.02.2023 | 22:55 | Equalizer Foundations | Code | 230 | Create Structure of the Equalizer Dinamically: 45 Columns / Text Node and 32 Beat Divs
21.02.2023 | 2:50 | Equalizer Functions | Code | 165 | Equalizer Starts Animation on Columns, Stores Timer Functions, 2000ms Reverse, Short Circuit Timers on New Function Calls
21.02.2023 | 13:30 | Design Head Stock | Design | 75 | Headstock Comprises of 5 Main Components, Upper / Lower Covers, 2 x Neck Support, Peg Placement
21.02.2023 | 14:45 | Cut Head Stock Material | Build | 115 | Cut, Sand Head Stock Elements #1 - #5
21.02.2023 | 16:40 | Adjusting and Gluing | Build | 110 | Adjust Sizes to Perfectly Fit Together
21.02.2023 | 20:15 | Sanding Corners | Build | 25 | Sand Corners 45 Degree
21.02.2023 | 20:40 | Drill and Triangles | Build | 60 | Drill Tuning Peg Holes and Small Triangles to Hold Screw in Position
22.02.2023 | 0:00 | Practice 2: General | Test | 30 | Some Base Notes are Left Highlighted, Needs Debugging
22.02.2023 | 0:40 | Debug Note Highlights | Code | 55 | The Highlight Removal was Incomplete and in Some Cases the Base String Highlight Stayed on (Fixed)
22.02.2023 | 1:35 | Work Monitor | Code | 110 | Create a Labour Monitor in Python Notebook
22.02.2023 | 13:30 | Drill Holes for Neck Strings | Build | 30 | Holes on Neck Base and Head Stock Triangles
22.02.2023 | 15:00 | String Base Support | Build | 40 | 3mm x 7mm x 10mm with Grooves 6 x 1.5mm and 45 Degree Angel and Paint
22.02.2023 | 16:00 | String Up Device | Build | 150 | Set Up Strings
22.02.2023 | 18:40 | Button Caps 1 | Build | 490 | Btn 1 - 90 (Cut, Mill 3.2mm Holes, Middle Groove and Paste)
23.02.2023 | 16:00 | Button Caps 2 | Build | 115 | 91 - 120 (Cut, Mill 3.2mm Holes, Middle Groove and Paste)
24.02.2023 | 4:30 | Strum Components Diagram | Design | 55 | Create a Diagram of the Main Components of the Strum Unit #1 - #5 and Springs and Levers
24.02.2023 | 13:15 | Paste Strings and Button Caps | Build | 65 | Paste Strings to the Button Caps to Provide Better Grip without Strings Slipping off Buttons
25.02.2023 | 14:55 | Strum Assembly Diagram | Design | 90 | A Comprehensive Projection Diagram of the Strum Unit
01.03.2023 | 19:00 | Toggle and LEDs Diagram | Design | 20 | Electrical Design of Console Body Inputs / Outputs
02.03.2023 | 11:00 | Extend Strum Options | Documentation | 25 | Research and Add Capacitive, Optical and Magnetic Strum Solutions
02.03.2023 | 11:30 | Strum Paragraph | Documentation | 25 | Write Strumming Paragraph
02.03.2023 | 12:50 | Lever Mechanism | Documentation | 55 | Lever Mechanism Diagram and Explanation
02.03.2023 | 13:50 | Toggle and LEDs Paragraph | Documentation | 15 | Small Paragraph about Toggle Necessary and LEDs Colour Meanings
02.03.2023 | 15:20 | Head Stock Diagram and Paragraph | Documentation | 175 | Head Stock Projection Diagram and Explanation Paragraph
03.03.2023 | 1:40 | User Activities Diagram | Design | 85 | Activity Diagram and Paragraph
03.03.2023 | 3:05 | Prototype Development Images | Design | 80 | Download and Transfer Images, Select Appropriate Ones and Crop Them to Fit in a Table of 3 Columns
03.03.2023 | 4:25 | Prototype Development Text | Documentation | 65 | Steps and Challenges
03.03.2023 | 19:05 | UX Paragraph | Documentation | 55 | Write UX Fundamentals Principles and Colour Palette Diagram and Explanation
03.03.2023 | 20:20 | App State Paragraph | Documentation | 35 | Advantages and Disadvantages of Global App State
04.03.2023 | 21:00 | JQuery Paragraph | Documentation | 50 | Explain Jquery Style Utility Functions and Code Snippets
05.03.2023 | 18:00 | Back End Paragraph | Documentation | 20 | Intro of RESTful Architecture Design
05.03.2023 | 18:30 | User Interaction | Documentation | 110 | Explain the Usage of JWT Tokens and Create a Login Request-Response Diagram
06.03.2023 | 16:00 | ER Diagram | Design | 120 | Basic Tables and Properties
07.03.2023 | 14:00 | ER Paragraph Intro | Documentation | 20 | Explain Stack Options (MERN)
08.03.2023 | 14:00 | ER Tables Explained | Documentation | 30 | Explain the Tables and Properties Briefly
08.03.2023 | 17:30 | Physical Materials Paragraph | Documentation | 85 | Table of Ranking of Physical Materials and their Properties and Explanation
08.03.2023 | 19:00 | Upload Images to Cloud | Documentation | 10 | Upload all 180 Images to Google Drive and Update the Link in the Documentation
08.03.2023 | 19:10 | Microcontroller Selection | Documentation | 45 | Compare Leonardo, Due and Mega (Table and Explanation)
08.03.2023 | 19:50 | Microcontroller Programming | Documentation | 30 | Initialising and Reading State, Sending Message (Code Snippets)
08.03.2023 | 20:20 | Protocols | Documentation | 45 | Expalin Midi, Binary, Textual and Digital and Chosen Protocol
09.03.2023 | 16:40 | Serverside Setup | Code | 20 | Install Express, Nodemon, Initialise Backend, add .gitignore
09.03.2023 | 17:00 | MERN Course - 1 | Tutorial | 45 | Take a Complete Node/Express/Mongo/TDD Course to be Able to Correctly Build the Backend of the App (Mosh Intro)
09.03.2023 | 18:20 | MERN Course - 2 | Tutorial | 25 | Node Architecture
09.03.2023 | 18:45 | MERN Course - 3 | Tutorial | 55 | Node Module System, Event Emitters, HTTP Module
09.03.2023 | 19:40 | MERN Course - 4 | Tutorial | 90 | NPM and RESTful Services with Express, Postman, HTTP Verbs, Joi
10.03.2023 | 20:15 | MERN Course - 4 Cont | Tutorial | 20 | Continue Validation (Use Joi@13.1.0!!! Breaking Changes in Further Versions)
10.03.2023 | 20:35 | Build User Request Sceleton | Code | 55 | Build the Sceleton Code for User GET, POST PUT and DELETE Requests
10.03.2023 | 22:10 | MERN Course - 5 | Tutorial | 55 | Advanced Express: Middlewares, Pipeline, Debug, ENV, Config
10.03.2023 | 23:05 | Restructure App | Code | 60 | Apply Routes (Index, User)
11.03.2023 | 0:10 | MERN Course - 6 | Tutorial | 75 | MongoDB, Mongoose
11.03.2023 | 1:25 | CRUD Users | Code | 60 | Create Functions for the Basic CRUD Operations for User Schema
11.03.2023 | 2:25 | MERN Course - 7 | Tutorial | 55 | MongoDB, Mongoose Data Validation
11.03.2023 | 3:20 | User Model | Code | 25 | Create the User Model and Joi Validation
11.03.2023 | 4:00 | Express Pipeline Paragraph | Documentation | 35 | Express Pipeline Explanation and Diagram
11.03.2023 | 4:35 | Complete User Routes | Code | 45 | Complete and Test User Routes with MongoDB Connection (To be Continued...)
11.03.2023 | 13:20 | Complete User Routes Continued | Code | 55 | Request GET/api/users/, GET/api/users/:id, POST/api/users{body}
11.03.2023 | 15:00 | Complete User Routes Continued | Code | 45 | Request PUT/api/users/id
13.03.2023 | 8:55 | Profile Model | Code | 90 | Create Profile Model and Validation
13.03.2023 | 13:00 | Profile Router | Code | 100 | Profile Routes: GET:api/profiles/:ID, POST:/api/profiles/{body}
14.03.2023 | 14:00 | Tabs Model | Code | 65 | Create Tabs Model Schema
14.03.2023 | 15:10 | Tabs Router | Code | 120 | Tabs Routes: GET:api/tabs, GET:api/tabs/:ID, POST:/api/tabs/:ID{body}, DEL:/api/tabs/:ID
14.03.2023 | 17:20 | Achievements | Code | 70 | Achievment Routes: GET:/api/achievements/, GET:/api/achievements/:NAME, POST:/api/achievements/{body}, and Rewise Status Response Codes
14.03.2023 | 21:15 | Profile-Achievements Relation | Code | 70 | Save Achievements as an Array of ObjectIDs, and Create Route PUT:/api/profile/:ID {body}
14.03.2023 | 22:30 | MERN Course - 8 | Tutorial | 50 | Data Relationship (Normalisation / Denormalisation), Populate, Transactions, ObjectID Generation
14.03.2023 | 23:20 | Improve Routes and Models | Code | 145 | Populate, Hide Password, Iterate and Validate PUT ObjectIDs for Subdocuments
15.03.2023 | 1:45 | MERN Course - 9 | Tutorial | 65 | Authentication and Authorization
15.03.2023 | 2:50 | Security Diagram | Documentation | 25 | Discrete Password Forms, Frontend Hashing, HTTPS, Encrypting and Salting, Comparing
15.03.2023 | 16:30 | Create Login and Auth | Code | 195 | Hash, Compare and Validate Password, JWT, Authorization, Admin Privilages
15.03.2023 | 20:55 | MERN Course - 10 | Tutorial | 60 | Handling and Logging Errors, Automated Testing and TDD
15.03.2023 | 21:55 | MERN Course - 11 | Tutorial | 75 | Unit Testing
15.03.2023 | 23:10 | Unit Tests | Test | 200 | Build Unit Tests
16.03.2023 | 4:00 | MERN Course - 12 | Tutorial | 55 | Integration Testing and TDD
16.03.2023 | 5:00 | Create Login Page | Code | 65 | Redirect to Login Page When No User Token Found
16.03.2023 | 15:30 | Login Validation | Code | 65 | Validate Edge Cases on Both Email and Password Inputs and Display User Message
16.03.2023 | 16:35 | Send GET:/ | Code | 85 | Connect to Localhost API Root
16.03.2023 | 18:00 | POST api/subscribe | Code | 140 | Create Subscribe Route, Get Email Info from ENV, Configure Email Account with App Passwords, Send Email
16.03.2023 | 21:00 | Confirm Email Link | Code | 50 | Create a Confim Link in the Email with JWT Token
16.03.2023 | 21:50 | Fix API Bugs | Troubleshooting | 30 | Refactor Steps of Authentication Login Register Btn Redirects to Register Page and Then Send Confirm Email
16.03.2023 | 22:20 | Create Register Page | Code | 210 | Create Register Page, Input Validation, Styling, Login Styling, Background and Gradients
17.03.2023 | 1:55 | Encryption Paragraph | Documentation | 90 | Research Frontend and Backend Hashing and Encryption
17.03.2023 | 3:25 | Create Profile Page | Code | 135 | Fix Up Issues: Missing Screws on Body and Neck, Contact Failures (B2 and Simultaneous A#2 D#3), Missing Supporting Element on Neck
17.03.2023 | 14:50 | Profile Page Validation | Code | 230 | Complete Form Validation, Avatar Selection, Valid Dates and Formats, Autocomplete Countries
17.03.2023 | 22:30 | Register a User | Code | 105 | Send Subsrcibe Request and Send User Info Via JWT, Create User and Profile
18.03.2023 | 0:15 | Complete Login / Logout Process | Code | 220 | Validate Registration on Backend, Send Token, Hash Password, Login User, Logout User
18.03.2023 | 3:50 | Document Backend | Documentation | 90 | API Routes Diagram, Explanation, 2 Phase Registration, Code Snippets
22.03.2023 | 10:35 | Compose - Restructure Tab Format | Code | 220 | Complete Restructure, Commenting, Debbuging…
22.03.2023 | 14:20 | Compose - Game Loop Timing | Code | 25 | Calculate Loop Timing from Music Tab Tempo
22.03.2023 | 16:30 | Compose - Focus Bar 1 | Code | 75 | Center Single Line Current Bar
22.03.2023 | 20:05 | Compose - Focus Bar 2 | Code | 245 | Center Multi Line Current Bar and Highlight Current Bar
23.03.2023 | 0:25 | Compose - Highlight Note | Code | 85 | Highlight Current Notes
23.03.2023 | 1:50 | Compose - Validate Tab | Code | 180 | Validate Tab Formatting before Load and Create Error Message
23.03.2023 | 4:50 | Compose - Name of Tempos | Code | 20 | Find Appropriate Latin Tempo Names for BPM Ranges
23.03.2023 | 5:15 | Compose - Play Notes | Code | 40 | Find Given Point in Current Bar's Start Position and Play Note Audio
23.03.2023 | 13:00 | Compose - Stop Notes | Code | 90 | Calculate Note Stop Delay and Call Timer for Each Playing Note
23.03.2023 | 14:55 | Compose - Note Placement Warning | Code
23.03.2023 |  | Safe Redirect | Code |  | Redirect Utility Function: Takes URL as Parameter, Saves User and Token on Local Storage, Redirect Page, Copies User in Global Var, Delete Storage
23.03.2023 |  | Registration - Email Duplicates | Code |  | Check DB for Duplicated User Emails Before Redirecting to Profile Page
23.03.2023 |  | Compose - Duration Notation | Code
23.03.2023 |  | Compose - Change Tempo | Code
23.03.2023 |  | Compose - Change Title/Artist | Code
23.03.2023 |  | Compose - Editable Notes | Code
23.03.2023 |  | Compose - DB Properties | Code |  | isPublised, No Album Cover Image / Avatar or Album Image Cover URL
23.03.2023 |  | Compose - Bar Pagination | Code
23.03.2023 |  | Compose - Repeat Section | Code
23.03.2023 |  | Compose - Save Tab | Code
23.03.2023 |  | Compose - Load Tab | Code
23.03.2023 |  | Compose - Record Guitar Input | Code
23.03.2023 |  | Index - Load User Info from DB | Code
|  |  | Total Minutes | 35140
|  |  | Total Hours | 585.6667