## Sheet1
# | Risk | Description | Probability | Severity | Action
1 | Scope Variation | Addition of unforeseen features. | Occasional | Marginal | Only add additional features if every requires met.
2 | Optimistic Schedule | Bad estimation of task executions. | Probable | Critical | Estimate optimistic and pessimistic schedule
3 | Facilities | Hardware parts are delayed or unavailable. | Remote | Critical | Order hardware part in advance of the assembly schedule.
4 | Finances | Higher hardware or software cost as expected. | Remote | Moderate | Create a hardware cost table in advance.
5 | Data Loss | Loss of project data or source code or documentation. | Occasional | Marginal | Frequent Data Backup (Flash Drive / Git Account)
6 | Legal | Legislation issues or patent collision. | Improbable | Critical | Check existing patents and technologies.
7 | QA | Failure of Quality Assurance, bugs. | Remote | Critical | TDD, code reviews, automated testing.
8 | Analysis | Incomplete or missing requirement details. | Remote | Moderate | Review Requirements
9 | Value | Inadaquate value analysis to measure progress. | Remote | Marginal | The project is not intended for commertial use in this phase.
10 | Safety | Food health and safety requirements | Remote | Catastrophic | Review and adhere electrical safety practices. | Probability | Frequent | Probable | Occasional | Remote | Improbable
11 | Development | Developing inaccurate user interface. | Occasional | Moderate | Prototyping, peer review and user acceptance testing | Severity | Catasthrophic | Critical | Moderate | Marginal
12 | Difficulty | Development technically too difficult. | Remote | Moderate | Technical analysis before project approval.
13 | Licence | Software Licence management and expiry. | Remote | Marginal | Licenses recently reviewed