## Sheet1
Date | Time | Task | Type | Duration in Mins | Comment
26.09.2022 | 22:20 | Idea and Concept | Research | 60 | The Fundamental Idea and Some Conceptualisation and Research on Existing Inventions
27.09.2022 | 14:55 | Arduino Tutorial | Tutorial | 90 | Arduino Electronic Basics - Voltagies and Currents
28.09.2022 | 19:05 | Arduino Tutorial | Tutorial | 95 | Arduino Electronic Basics - Resistance and Microchip
29.09.2022 | 14:55 | Arduino Tutorial | Tutorial | 80 | Arduino Electronic Basics - First Circuits and Lab
29.09.2022 | 16:00 | Arduino Tutorial | Tutorial | 80 | Arduino Electronic Basics - Analog and Digital Signal and Components
30.09.2022 | 21:10 | Arduino Tutorial | Tutorial | 130 | Arduino Programmin Basics - Serial, PinMode, Basic C++ and Lab: LED Series
30.09.2022 | 23:20 | Arduino Tutorial | Tutorial | 95 | Arduino Programmin Basics - Functions and LED State Lab
01.10.2022 | 18:15 | Arduino Tutorial | Tutorial | 80 | Arduino Programmin Basics - 4 Different LED and Speaker Lab Project
01.10.2022 | 21:00 | Arduino Tutorial | Tutorial | 100 | Arduino Programmin Basics - Analog PINS, ADC, Speaker Frequency with Potmeter Lab
04.10.2022 | 18:30 | First Keyboard | Experiment | 120 | Create First Arduino Keyboard with 8 Keys that Can be Pressed Simultaneously. Keyboard State is Translated into a Byte.
05.10.2022 | 23:15 | Project Document Boilerplate | Documentation | 240 | Document Cover Page, Image and Quote, Complete Sketch of Paragraphs and Structure, Header, Footer, Pagination, Styling
06.10.2022 | 3:30 | Project Introduction | Documentation | 140 | First Sketch of the Introduction Section / Research on Instrument Taxonomy, History, Sound and Audio
06.10.2022 | 9:20 | Project Introduction | Documentation | 50 | First Version of the Background Paragraph
08.10.2022 | 16:00 | Project Introduction | Documentation | 60 | Outline of Specifications and Terminology: Chord, Riff, Monophone/Polyphone
09.10.2022 | 13:00 | Existing Technologies | Research | 190 | Existing Technologies, Guitar Hero, MI Digital Guitar, RockSmith and their specifications and Comparision Section
09.10.2022 | 22:00 | Project Aim and Objectives | Documentation | 80 | Research Gap, Aim and Objectives Paragraph, Literature Review: Sketch Strum vs Strumbar Task Plan
10.10.2022 | 12:00 | Research on Possible Solutions | Research | 45 | Read about Keyboard Matrixes and Keypress Ghositng, Forse Sensitive Resistors, Guitar Fret Distance Calculation Algorithms
11.10.2022 | 19:00 | Research Keyboards | Research | 80 | Research on Keyboard Scanning and Create Flowchart
11.10.2022 | 23:00 | Research Keyboards | Research | 240 | Research Key Switch Interface Design: Buses, Matrix, Debouncing
12.10.2022 | 3:30 | Research Fret Distances | Research | 210 | Research the Calculation and Algorithm of Fret Distances Create Diagrams and Paragraphs
12.10.2022 | 16:30 | Correcting Citations | Documentation | 25 | Correct citations with Microsoft World's automatic features
13.10.2022 | 10:30 | User Requirements | Research | 30 | Research User Requirements Formats and Best Practices
13.10.2022 | 12:30 | Prerequisites | Documentation | 30 | Write Prerequisites and Refine Concept Diaqgram
13.10.2022 | 13:30 | User Requirements | Documentation | 90 | User Requirements Hardware, Software, Authentication, Wireframes
13.10.2022 | 17:00 | User Requirements | Documentation | 170 | User Requirements: Sign in, Home Page Wireframes
13.10.2022 | 20:00 | User Requirements | Documentation | 240 | User Requirements: Play Menu Option, Play Wireframes, Experiment with Scoring Ideas, Scoring Table
14.10.2022 | 2:00 | User Requirements | Documentation | 130 | User Requirements: Complete
14.10.2022 | 10:00 | Constraints | Documentation | 55 | Constraints Chapter: Scope and Limitations
14.10.2022 | 14:00 | Cost, Marketability, Feasibility | Documentation | 220 | Chapters Cost (research prototype parts for estimation), Target Audience, Marketability, Feasibility and Social Aspects for Success
|  |  | Minutes | 3255
|  |  | Hours | 54.25
|  | Arduino Experiment 4X4 Matrix | Experiment | TBA | Create an Arduino 4X4 Numpad as a Preparation for the Complete Fret Keyboard